## week1
Computer Science 2 Project | Team Members: | Noah Jarelle Jorda
Group Progress Report |  | Jonash Miguel Aidan Cobico
3rd Quarter
Week 1 - Jan 16, 2026 (covers week 1-3 of proj sched)
GOAL State your goal for the Week | DATA COLLECTED State/list the data collected relevant to your project | PROGRESS State the progress you have made so far by the end of the week
- Develop the code structure | N/A | N/A
STRENGTH
Effieciency in code development.
AREAS FOR DEVELOPMENT
Time management
STRATEGY FOR SUCCESS
Get most of the ideas in one go.
Plan little by little.

## week2
Computer Science 2 Project | Team Members: | Noah Jarelle Jorda
Group Progress Report |  | Jonash Miguel Aidan Cobico
3rd Quarter
Week 2 - Jan 23, 2026 (covers Week 4)
GOAL State your goal for the Week | DATA COLLECTED State/list the data collected relevant to your project | PROGRESS State the progress you have made so far by the end of the week
-Continue developing code | N/A | Started developing the start of the code
STRENGTH
Function creation and keeping track of tasks
AREAS FOR DEVELOPMENT
Consistency and focus
STRATEGY FOR SUCCESS
Same as week 1

## week3
Computer Science 2 Project | Team Members: | Noah Jarelle Jorda
Group Progress Report |  | Jonash Miguel Aidan Cobico
3rd Quarter
Week 3 - Jan 30, 2026 (covers week 5)
GOAL State your goal for the Week | DATA COLLECTED State/list the data collected relevant to your project | PROGRESS State the progress you have made so far by the end of the week
Continue on developing code |  | Built more than 50% of code
Put neccessary comments
STRENGTH
Consistency
AREAS FOR DEVELOPMENT
Knowledge on code development
STRATEGY FOR SUCCESS
Continue development of code little by little.

## week4
Computer Science 2 Project | Team Members: | Noah Jarelle Jorda
Group Progress Report |  | Jonash Miguel Aidan Cobico
3rd Quarter
Week 4 - Feb 6, 2026 (covers week 6)
GOAL State your goal for the Week | DATA COLLECTED State/list the data collected relevant to your project | PROGRESS State the progress you have made so far by the end of the week
Finish atleast 70% of the code |  | Finished developing 65% of the code
STRENGTH
Same as week 3
AREAS FOR DEVELOPMENT
Knowledge on code development
STRATEGY FOR SUCCESS
Same as week 3